## Risk Assesment
Ticket: |  | Risk Assesment |  |  | Date:
Risk | Risk Statement | Response Stratogy | Objectives |  | Baseline |  |  | Future Impact
[5 empty] | Liklyhood | Impact | Risk Level | Liklyhood | Impact | Risk Level
Operational Risks
Implemented tables dont work | Not Yet Defined | Run tests on them to assure the data is being passed through correctly | Assure data is beeing added or removed form created tables | Improve the functionality of the tables to provide the user a more responcive experiance | Unlikly | Very High | 1 | Impossible | Very High | 3
Loosing the user amongst an over use of pages | Reducing Risk | Minimise the use of html where possible. | asure that the pages on data is as expected. | Minimise or remove pages where interaction by the user is not nessasery | Likely | Low | 4 | Unlikly | Low | 1
Over Reaching | Reducing Risk | Minimise the user of table data to meet to the brief. | Make only tables required to meet the breif. | Expand where nessasery once originals are implemented | Likely | Middle | 3 | Unlikly | Very Low | 1
Data Loss | Not Yet Defined | Table data being reset by server or not saved | Assure all links work correctly | run pytests to assure functions work as expected | Unlikly | High | 6 | Unlikly | Low | 3
File corruption | Reducing Risk | Use alternative branches to assure the master remains a working version | dont damage the master version | git bash checkout | Likely | Very High | 8 | Unlikly | Very High | 4
User is unable to reach site | Accepting Risk | Assure the servers are on before implementing tests or presenting | assure the site is operational before demonstrations |  | Unlikly | High | 5 | Unlikly | Middle | 1
Project hacking | Reducing Risk | Hide important content data | do not display username or password in any publicly accessable documentation | hide all sensative data from a user, malisious or inicent | Unlikly | Very High | 10 | Unlikly | Very High | 3
duplication | Accepting Risk | Create the site to meet to objective before refineing | meet the base objective | filter out content to prevent duplication | Likely | High | 4 | Impossible | Low | 1
stranded data | Reducing Risk | Removal of a user or film could leave data within tables that dont hold a relationship. | before removing a film or user, assure delete functions work on the Collections table first | intergrate the delete function into the removal process for these tables. | Likely | Very High | 5 | Impossible | Low | 1
content exceeding field allowance | Accepting Risk | Create fields with a reasonable field size | assure general film titles fit the field without ussue | refine the input proccess to better limit the content wanting to be submitted | Likely | Middle | 3 | Likely | Middle | 3
user error | Reducing Risk | Clearly mark boxes and/or buttons to reduce human error | make buttons and boxes with cleare content titles | on data defining options, create a confirm field | Likely | High | 6 | Likely | High | 4
Build errors | Reducing Risk | Integrate the site with Jenkins to reduce the risk of starting the server without pulling changes and working on somthing not broke | make the sites pipeline more responcive | Have the process run without the need of intervention | Unlikly | Middle | 3 | Unlikly | Middle | 4
Test intergration fails | Reducing Risk | Use a checklist | focus on areas important to the objective | refine the tests | Likely | High | 6 | Impossible | Middle | 10
Test coverage | Reducing Risk | Attempt to cover all aspects | have tests that check the CRUD functions | expand the testing to focus on buttons and other visual aspects | Likely | Middle | 4 | Unlikly | Middle | 3
Coverage not 100% | Accepting Risk | some lines are not tetsed | reach 85+% | 90+% | Unlikly | Low | 2 | Unlikly | Low | 4
Unfinished documentation | Accepting Risk | Do my best to update documentation on each proccess i undergo | make notes | after each implementation, add to documentation | Likely | Middle | 4 | Likely | Middle | 2
knowledge | Reducing Risk | Make notes and expand knowledge | Create the miniaml site before expanding | expand on the site | Likely | High | 6 | Unlikly | Middle | 4
| - |  |  |  | - | - | - | - | - | -
Financial Risks
Leaving the Servers on over night | Accepting Risk | Set an alarm to shut the servers down when not being used to save on credit | save money | code and test without the use of spending money | Likely | Low | 6 | Unlikly | Low | 3
| - |  |  |  | - | - | - | - | - | -
Objective Risks
The project could fail to meet the requirments set by brief. | Reducing Risk | create a check list of things needed and without applying filters assure the funtions requested are implemented. | Intergrate CRUD Functions | Refine site functionality to assure they meet to the sites needs aswell as the objective. | Unlikly | High | 4 | Unlikly | Very High | 8
| - |  |  |  | - | - | - | - | - | -

## Key
- | - | - | -
Impossible | Very Low | 1 | Not Yet Defined
Unlikly | Low | 2 | Reducing Risk
Likely | Middle | 3 | Accepting Risk
Very Likely | High | 4
Extreemly Likely | Very High | 5
6
7
8
9
10